## Sheet1
Id	Research Ethics Committee Reference Number	Integrated Research Application System Number	Submission Type	Name of Trial	Date of Receipt of Valid Research Application	Date of NHS Permission	First Patient Recruited?	Date of First Patient Recruited	Duration between VRA and NHS Permission	Duration between NHS Permission and First Patient	Duration between VRA and First Patient	Benchmark Met	Date Study Initiated	Date Site Invited	Date Site Selected	HRA Approval Date	Date Site Confirmed By Sponsor	Date Site Confirmed	Non-Confirmation Status	Date Site Ready To Start	A - Permissions delayed/denied	B - Suspended by sponsor	C - Closed by sponsor	D - Sponsor Delays	E - Staff availability issues	F - No patients seen	G - No patients consented	H - Contracting delays	I - Rare diseases	J - Other	Comments	Reasons for delay correspond to:
82814	15/YH/0242	173243	NHS Permission	A 21-week, open-label, randomized, controlled, parallel-group, multi-center studyevaluating the efficacy and safety of HOE901-U300 administered according to adevice-supported treat-to-target regimen versus routine titration in T2DM patients	15/12/2015	19/01/2016	Yes	07/03/2016	35	48	83	No	22/01/2016	03/03/2015	07/04/2015		16/12/2015	21/12/2015	Please Select...	02/02/2016				Y				Y			delay due to sponsor not giving green light	Sponsor
82815	15/LO/2066	193084	NHS Permission	PIONEER - 4222	03/02/2016	18/03/2016	Yes	10/05/2016	44	53	97	No	03/02/2016	09/09/2015	10/11/2015		14/03/2016	01/04/2016	Please Select...	01/04/2016	Y				Y			Y			Delays due to staffing issues	NHS Provider
82823	15/SC/0256	177204	NHS Permission	INEXAS	01/09/2015	11/09/2015	No		10			No	17/09/2015	17/02/2015	24/03/2015		16/09/2015	30/09/2015	Please Select...	30/09/2015	Y						Y	Y			Delays due to data transfer issues	NHS Provider
82824	15/YH/0239	179158	NHS Permission	LIBERTY	01/09/2015	11/09/2015	No		10			No	24/09/2015	01/09/2015	01/09/2015		20/07/2015	21/07/2015	Please Select...	25/09/2015	Y						Y	Y			Delays due to data transfer issues	NHS Provider
82825	14/NE/1102	160814	NHS Permission	IMPACT	07/09/2015	11/09/2015	No		4			No	08/10/2015	07/09/2015	07/09/2015		05/10/2015	12/10/2015	Please Select...	12/10/2015	Y						Y	Y			Delays due to data transfer issues	NHS Provider